## Manual Chart
Universal Cinema Listings - GANTT CHART
TASK NO. | TASK NAME | START DATE | DUE DATE | DURATION (WORK DAYS) | % OF WORKLOAD | W1: 8th Oct |  |  |  |  | W2: 15th Oct |  |  |  |  | W3: 22nd Oct |  |  |  |  | W4: 29 Oct |  |  |  |  | W5: 5th Nov |  |  |  |  | W6: 12th Nov |  |  |  |  | W7: 19th Nov |  |  |  |  | W8: 26th Nov
[6 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
1 | Project Proposal | 9th Oct | 26th Oct | 17 | 7% | bar: W1: 8th Oct T to W3: 22nd Oct F
2 | Research & Requirements | 9th Oct | 14th Dec | 68 | 20%
3 | Write Up Functional Specification | 9th Oct | 30th Nov | 53 | 15%
4 | Presentation of Project Proposal | 5th Nov | 9th Nov | 5 | 1% | bar: W5: 5th Nov M to W5: 5th Nov F
5 | Assess Results of Proposal Presentation | 13th Nov | 13th Nov | 1 | 5% | bar: W6: 12th Nov T
6 | Design Mock Interfaces | 13th Nov | 23rd Nov | 10 | 2% | bar: W6: 12th Nov T to W7: 19th Nov F
7 | Begin SSADM Diagrams | 13th Nov | 23rd Nov | 10 | 2% | bar: W6: 12th Nov T to W7: 19th Nov F
8 | Prepare Development Environment | 3rd Dec | 7th Dec | 5 | 1%
9 | Develop Prototype Web Scraper Script | 3rd Dec | 14th Dec | 11 | 3%
10 | Develop Script for Getting Cinema Data | 3rd Dec | 14th Dec | 11 | 3%
11 | End of Semester 1 | 14th Dec | 14th Dec | 1 | 1%
12 | Inter-Semester Holidays | 15th Dec | 6th Jan | 23 | 8%
13 | Exam Period | 7th Jan | 19th Jan | 13 | 6%
14 | Start of Semester 2 | 28th Jan | 28th Jan | 12 | 3%
15 | Develop Database for Cinema Data | 21st Jan | 1st Feb | 12 | 3%
16 | Develop Graphical User Interfaces | 28th Jan | 8th Feb | 12 | 3%
17 | Develop Filtering Module | 28th Jan | 8th Feb | 12 | 3%
18 | Develop Test Data | 4th Feb | 8th Feb | 5 | 1%
19 | Integrate Web Scraper with UI | 11th Feb | 15th Feb | 5 | 1%
20 | Integrate Updater with Application | 11th Feb | 15th Feb | 5 | 1%
21 | Testing Phase | 18th Feb | 22nd Feb | 5 | 1%
22 | Perform User Experience Analysis | 25th Feb | 1st Mar | 5 | 1%
23 | Finish SSADM | 25th Feb | 1st Mar | 5 | 1%
24 | Make Video Walkthrough | 25th Feb | 1st Mar | 5 | 1%
25 | Write up User Manual | 27th Feb | 3rd Mar | 5 | 1%
26 | Write up Tech Manual | 27th Feb | 3rd Mar | 5 | 1%
27 | Survey All Github Items | 4th Mar | 6th Mar | 3 | 1%
28 | Gather and Resolve All Deliverables | 7th Mar | 8th Mar | 2 | 1%
29 | Final Performance Check | 8th Mar | 8th Mar | 1 | 1%
30 | Demonstrate the Project | 11th Mar | 22nd Mar | 11 | 3%
|  |  |  | 338 | 100%
[6 empty] | W9: 3rd Dec |  |  |  |  | W10: 10th Dec |  |  |  |  | W11: 17th Dec |  |  |  |  | W12: 24th Dec |  |  |  |  | W13: 31st Dec |  |  |  |  | W14: 7th Jan |  |  |  |  | W15: 14th Jan |  |  |  |  | W16: 21st Jan
[6 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
[6 empty] | W17: 28st Jan |  |  |  |  | W18: 4th Feb |  |  |  |  | W19: 11th Feb |  |  |  |  | W20: 18th Feb |  |  |  |  | W21: 25th Feb |  |  |  |  | W22: 4th Mar |  |  |  |  | W23: 11th Mar |  |  |  |  | W24: 22nd Mar
[6 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F